## team
FTR Team member
# | Name | Surname | Role | email | Employee ID | Citizen ID | Phone | Company
1 | Wathanaporn | Sriprapaipong | PM/Scrum Mater | wathanaporn@fujitsu.com | 9198 | 3100700560215 | 0891231076 | FTH
2 | Jimmy | Mochtar Chandra | DevSecOps PIC | jimmy.ch@fujitsu.com | 8377 |  |  | FTH
3 | Kittanai | Chamvijit | SA | kittanai@fujitsu.com | 9440 | 1100700126497 | 0988964663 | FTH
4 | Vithan |  | Technica Lead | vithan@zerobug.co.th
5 | Waiyawut |  | UX/UI Design
6 | Camin |  | Mobile Senior PG
7 | Chanchai |  | Mobile PG
8 | Kittipon |  | App Senior PG
9 | Kana |  | App PG
10
test

## Activities
Agile Activities
Sprint N
Week | 1 |  |  |  |  | 2
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task Role Loc. | 1. Tsak breakdown - Screen (input/prc/output) - Batch (input/prc/output) - Report (input/prc/output) - DB Design (ER : Key) - Unit Test by Function - Prepare Unit Test Data - Automate Test (as acceptance picked from backlog) 2. Assign Task PIC @ Duration 3. Summarize and confirm duration | 1. Daily Scrum (10:00am) - Have done - To done - Problem vs Contermeasre | [7 empty] | 1. Acceptance show case (2h)
- Manual Test of Sprint N
- Regression Test by Robot for prev, sprint N
2. Sprint Review (1h)
|  | PO, PM, BA, QA, TL, PG (Senior) | [7 empty] | - New CR
|  | 2. DB Structure | [7 empty] | - Refine backlog next sprint
|  | TL | [7 empty] | - Final "Definition of Done"
|  | 3. Coding by function | [7 empty] | US, PO, PM, BA, QA, TL, PG
|  | 4. Unit Test | [7 empty] | TDEM : Half day agternoon
|  | TL,PG | [7 empty] | 3, Sprint Retrospective (1h)
|  | 5. Prepare and Execute Acceptance Test Scnario + Test Case for function test (Spring N) | [7 empty] | - Team Sharing
|  | 6. Coding Robot + Prepate Robot data (Acceptance data in "Definition of Done") (Sprint N-1) | [7 empty] | - Improve/ Refine process
| PO, PM, BA, QA, TL, PG (Senior) | QA | [7 empty] | PO, PM, BA, QA, TL, PG
| TEDM: All day, 1st day of Sprint N | 7.Deliverable Documentations (Sprint N-1) | [7 empty] | MS Team
SA
MS Team
8. Work on sprint n+1 (Grooming & Iteration Planing : refer intiation phase)
US, PO, PM, BA, QA(if required), TL(if required)
TDEM: Please break activity and output of Write Backlog, Grooming, Iteration Plan *** Half day of 2nd and 5th day in Sprint N required TDEM-user to join meeting.
For we can manage Room reservation and make appointment with user

## task list
FTR Task Plan
[6 empty] | Oct | [15 empty] | Nov
No. | Task | Target Date | PIC |  | Remark | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | List team member for Jira account |  | FTH
2 | Jira account creation |  | TDEM
3 | Define Project owner/Key user/IS |  | TDEM
4 | Submit team info for VPN and network access |  | FTH
5 | Provide VPN and network access for team |  | TDEM
6 | Infra handover |  | TDEM
7 | Kick off (FTH session) - Dev methodology - agile activities sharing - organization |  | FTH/TDEM | U
8 | Define business process As IS vs To Be |  | TDEM / FTH | U | As IS business process by TDEM
9 | Define Personas |  | TDEM | U | Define user role in application
10 | Define DOR, DOD |  | FTH/TDEM | U
11 | Confirm business requirement |  | FTH/TDEM | U | sample dashboard, report & summary report
12 | Define interface type |  | FTH/TDEM | U
13 | Identify main user stories from Personas need - break EPICS into high-level - sort user stories by priority (MoSCoW) - Define high level sprint#1, sprint#2 and SprintN |  | FTH/TDEM | U
14 | Quick wireframe with business user |  | FTH | U
15 | Initial backlog/sizing walkthrough |  | TDEM / FTH | U
16 | Choose top priority product backlog |  | TDEM / FTH | U
17 | Top priority user stories creation & grooming |  |  | U
18 | Dev environment network checking |  | FTH
19 | Technical preparation - Setup and prepare dev server - POC - DB design |  | FTH
20
21
22
23
sprint plan
| git lab account |  | Jimmy
management doc
biweekly - sprint weekly report
DR - sprint 5 (release 1 CRR project)
Performance test

## DoR
DoR |  | DoD
No | Detail | No | Detail
1 | INVEST principles are met: Independent, Negotiable, Valuable, Estimatable, Small & Testable | 1 | All code is developed and published on dev environment
2 | Is mapped as a step in business process diagram | 2 | Unit test passed and confirmed by TL
3 | Is prioritized based on MoSCow | 3 | Acceptance criteria met
4 | Is confirmed and clarify with user then everyone are aligned on what exactly to build | 4 | Product Owner accepts the User Story.
5 | There must be at least one accptance criteria in user stories. | 5 | demo
6 | The User Story is not blocked from the beginning by any internal or external dependency. | 6
7 | Expected Demo for the User Story when appropriate is understood and commited by the team | 7
8 | Test case/scenarios are defined | 8
9 | Meaningful and comprehensive test data is available | 9
10 |  | 10
11 |  | 11
12 |  | 12
13 |  | 13
14 |  | 14
15 |  | 15
16 |  | 16
17 |  | 17
18 |  | 18
DOR | screen design
report layout
batch interface format
test data if need
DOD | test result with no defect

## InterfaceType
FTR Interface Type
# | Interface List | Type of IF | Remark
1 | EMP Data (SAP-HR)
2 | EMP Active Directory
3 | O365
4 | TASTIS
5 | KPI Data
6 | Claim Data
7 | Customer Complain
8 | Travelling Claim
9 | Dealer Data

## Sprint 0
Epic
TODO | IN Process | DONE | REVIEWD
Break Down Screen
Break Down Batch
Break Down Report
Break Down Database
Break Down Prepare Robot Data
Break Down Robot
Story
Break Down Screen
Type: Bussiness
Output: Rquriement for screen
Split up into 2 group
1. Web UI
2. Mobile Application UI
Web UI
1. Login
2. Questionnaire Information
3. Download Report
4. User Management ** User Information, User Auterization
5. Role Management
6. Information management ** Best Practice, information
Mobile Application UI
1. Login
2. My Tasks
2.1 Trip Planning
2.2 Message
2.3 Report
2.4 Information
3. Manager
3.1 Assignment
3.2 Approval
4. Notification
Story
Break Down Batch
Type: Bussiness
Output: Rquriement for batch
Split up into 3 group
1. Batch for Web
2. Batch for Mobile Application
3. Backend API
Batch for Web
1. Login
2. User Management
3. Role Management
Batch for Mobile Application
1. Login
2. Registration
3. Forget Password
3. Self Trip Planning
4. Trip Management
5. Notification Search
6. Chat Search
7. Approve Search
8. Calendar
9. Message Communication
10. Report Screen
Backend API
1. Customer Complain
2. ABIZ
3. KPI Data
4. Travelling Claim
5. Dealer Data
6. EMP Data
7. EMP Active Directory
8. Office 365
9. Push Notfication
10. FTR Report
11. AD Hoc Report
Story
Break Down Report
Type: Bussiness
Output: Rquriement for report
Report is Real Time report
1. Field Trip Reoirt
1.1 Individual report
1.2 Summary report
2. ADHOC report
Story
Break Down Database
Type: Bussiness
Output: ER Diagram
Discuss in Database diagram
Story
Break Down Prepare Robot Data
Type: Bussiness
Output:
Discuss in Data for unit test
Story
Break Down Robot
Type: Bussiness
Output:
Discuss in unit test

## Sprint 1
Epic
TODO | IN Process | DONE | REVIEWD
Create Database Entity
Create Web
Create Moblie Application
Story
Create Database Entity
Type: Development
Output: Database class
Create Database Entity form ER Diagram
Story
Create Web
Type: Development
Output: Application in Web
Create in Web Application site
1. Login crete login service for web to Assign role and authority for user
2. User management
create service for user management (Add new user, update, Delete)
3. Role management
create service for role management (Update role to user)
Story
Create Moblie Application
Type: Development
Output: Moblie Application UI divide by user role
Create in Moblie Application site
1. Login crete login service get role and authority user
My Task for user in role normal user, Manager, for user in role manager and check authority user in Application
2. Profile
get user profile to show and user can change a user image profile
3. Config

## Sprint 2
Epic
TODO | IN Process | DONE | REVIEWD
Trip Planning Service
Story
Trip Planning Service
Type: Development
Output: Trip Planning Service and UI
Create Trip Planning Service
- Role User Create Trip plan
- Role User can Review and check Result Trip plan request
- Role Manager Create Trip plan to assign to user
- Role Manager Approve trip plan form user request

## Appendix
https://www.figma.com/proto/ymmniXH1RsgYJiRrMebnmA/Field-Trip?node-id=30%3A1282&scaling=scale-down&page-id=0%3A1&starting-point-node-id=22%3A887&show-proto-sidebar=1